## Sheet1
Feb 24-28 | March 3-7 | March 10-14 | SPRING BREAK | March 24-28 | March 31 - April 4 | April 7-11 | April 14-18 | April 21-25 | April 28 - May 2
Assemble base | PROGRESS PRESENTATION |  |  | PIR Sensor Testing |  | PROGRESS PRESENTATION |  |  | CAPSTONE SHOWCASE
Assemble components onto base | Polishing base (from glue) | PIR sensors |  | Sound sensor functionality |  | Final Print Deadline | Deadline for poster?
Start navigation programming | Assemble components onto base | Motors encoders |  | Motor encoders
Test sensor interference | Testing locatiomotion
Start PID (turning)